## Sheet1
[8 empty] | Aug 10 |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
Week
Stage | Tasks | [5 empty] | Day(s) Used | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Project Initiation:
1 | (1. 1) |  | PTB and KBS committed to initiate the projuect. |  |  |  | 4
System Specifications And Requirements And UI And Functionalities Confirmation:
2. & 3. | (2. 1) |  | System requirements' specification finding and study |  |  |  | 25-30
System requirements' specification doucumentation:
| (3. 1) |  |  | 1.) UI and functional process diagram
- Ticketing Machine System
- Management Information System
- Input UI
- Reportings
- Interfaces between System Components
- User Access Controls
| (2. 2) |  |  | 2.) Details biz operation process flow diagram.
- Ticketing Machine System
- Operational Workflow
3.) First level data requirements documented.
Database Structure
Submit Above Items to PTB for:
1.) User walkthrough and review.
2.) User acceptance.
3.) User feedback and variation.
System specifications and functionalities refinement process meeting.
Refinement tasks for above items
Submit refined system requirements' specification documentation
for PTB second round walkthrough, review and final acceptance.
4 |  | Documentation of Stage-2 And Stage-3:
| (4. 1) |  | According to the agreed outcome from stage-2, the complete MIS analysis |  |  |  | 7
and design done and documented.
| (4. 2) |  | The output from stage-3 are as follows:
1.) Database schema.
2.) Functional interface design.
3.) Input and output interface design.
4.) Reporting format design.
5. & 6. |  | System Development And Programming And System/Technical Testing: |  |  |  |  | 75
Programming logic and development commit at this phase.
Parallelly the system testing will be carried out as per functional requirement planned.
7 |  | User Traning And User Acceptance Test: |  |  |  |  | 25-30
Once system testing completed, KBB will conduct the user training.
During the user training stage, the user acceptance test process will carry out at the same time.
By the completion of user acceptance test, the quality assurance is done.
8. & 9. |  | System Implementation & Deployment And System Live Run
Completed system installation, configuration & commissioning to PTB networking
platform for live run.
Live run.
10 |  | Post Implementation Review:
Weekly post implementation review done.
Outcome from the review will serve for eenhancement and continuous improvement.